## Milestones
Name | FAST Lab Undergrads
Project | Convolutional Neural Net for SI Cancellation
Milestones
Week No. | Planned | Actual
2.1 | Architecture and Git Setup
2.2 | Decide on handshakes and coordinating between layers
2.3 | Fully-connected layer behavior functional
3.1 | Convolutional layer behavior functional
3.2 | Batch normalization layer functional
3.3 | Global Average Pooling layer behavior functional
3.4 | FPGA Data collected (major milestone before JCATI)
3.5 | JCATI Conference April 13th
4.1 | SAPR timing constraints written for 45nm
4.2 | Data review from JCATI
5.1 | Architecture of transverse matrix for back-propagation done
5.2 | 45nm STA done
Design Review Targets: 6.1 | FPGA Data collected, STA for 45nm done
7.1 | APR: RAM blocks placed
7.2 | Back-propagation module outputs correct
8.1 | Synthesis and APR
8.2 | Back-propagation writeback functional testing complete
8.3 | Final STA
8.4 | Post-SAPR Simulations

## Key Tasks
Task | Start Date | End Date | Dependencies? | Complete? | Assignee
Implement ROM | 2023-03-27 | 2023-03-30 | N/A | true | Alex
Implement Fully-Connected Layer | 2023-03-27 | 2023-04-06 | ROM | true | Alex
Implement Convolutional Layer | 2023-03-29 | 2023-04-08 | ROM | true | Alex
Implement Batch Normalization Layer | 2023-03-29 | 2023-04-10 | ROM |  | Eugene
Parametrize ROM | 2023-04-06 | 2023-04-10 | ROM |  | Alex
Small-sample Testing | 2023-04-05 | 2023-04-12 | ROM, some layers |  | Alex, Eugene
Combine layers | 2023-04-07 | 2023-04-10 | ROM, all layers |  | Alex, Eugene
Combine Testing | 2023-04-09 | 2023-04-12 | ROM, all layers |  | Alex, Eugene
Matlab Comparison, Testing | 2023-04-11 | 2023-04-17 | Combine Testing |  | Alex, Eugene
FPGA Timing Constraints | 2023-04-11 | 2023-04-17 | N/A |  | Alex, Eugene
FPGA Implementation | 2023-04-17 | 2023-04-24 | FPGA Timing, Matlab Comparison |  | Alex, Eugene
FPGA Data | 2023-04-24 | 2023-04-26 | FPGA Implementation |  | Eugene
Synthesis & Timing | 2023-04-11 | 2023-04-30 | Matlab Testing |  | Alex, Eugene
APR: PPA | 2023-05-01 | 2023-05-12 | Synthesis |  | Alex, Eugene
Stretch goal: Wireline Transceiver | 2023-04-17 | 2023-05-29 | N/A |  | Alex, Eugene
Stretch goal: Back-propagation | 2023-04-27 | 2023-06-01 | Matlab Testing |  | Eugene
Stretch goal: Integrate & Co-sim | 2023-05-14 | 2023-06-05 | At least 1 stretch goal |  | Alex
Final Report | 2023-04-30 | 2023-06-07 | FPGA Data |  | Alex, Eugene